## SAP on AWS Go-Live Check list
1 | SAP Support |  | % Complete | Customer Notes | AWS Review | Status
1.1 | AWS Support Agreement | SAP on AWS is only supportable if an AWS support agreement ("Business Support" or "Enterprise Support", both fee-based) is in place. Refer to 1656250 - SAP on AWS: Support prerequisites. |  |  |  | R,Y,G (Colors)
1.2 | AWS Monitoring | The AWS Data Provider collects the required performance and configuration data from a variety of sources including the EC2 API, EC2 Instance Metadata Service and AWS CloudWatch. This must be installed to ensure SAPOSCOL receives necessary data and is a requirement for Production Support. AWS CloudWatch Detailed Monitoring must be activated so that the required AWS metrics are provided in one-minute intervals. SAP Enhanced Monitoring must be on and the SAP Host Agent must be at a sufficient level. Refer to: 1656250 - SAP on AWS: Support prerequisites.
1.3 | AWS Certified Instance Types | AWS EC2 instance types listed in note 1656099 are supported in 2-tier or 3-tier configurations and can be used as application server(s) or pure database server(s). They have been sized through publicly available standard benchmarks (see https://www.sap.com/solution/benchmark/appbm/cloud.html). Refer to: 1656099 - SAP Applications on AWS: Supported DB/OS and AWS EC2 products.
1.4 | OS / DB Type | Database and OS Vendors have differing requirements in relation to support of SAP and on AWS. AWS advises that customers refer to applicable SAP notes and confirm license agreements and version end of life.
2 | Setup
2.1 | Account Structure | For key workloads such as SAP consider a multi account strategy to reduce the blast radius and ensure administrative isolation.
2.2 | VPC Construct | Amazon Virtual Private Cloud (Amazon VPC) enables you to launch Amazon Web Services (AWS) resources into a virtual network that you've defined. This virtual network closely resembles a traditional network that you'd operate in your own data center, with the benefits of using the scalable infrastructure of AWS. https://aws.amazon.com/documentation/vpc/ A VPC endpoint enables you to privately connect your VPC to supported AWS services and VPC endpoint services powered by PrivateLink without requiring an internet gateway, NAT device, VPN connection, or AWS Direct Connect connection. Traffic between your VPC and the other service does not leave the Amazon network.
2.3 | Naming Standards | Defining a naming standard up front that is flexible, consistent and clear is critical when it comes to operating systems in cloud. This is not constrained to hostname, but also virtual names and other AWS resource names.
2.4 | Tagging | Amazon Web Services (AWS) allows customers to assign metadata to their AWS resources in the form of tags. Each tag is a simple label consisting of a customer-defined key and an optional value that can make it easier to manage, search for, and filter resources. Although there are no strict requirements for types of tags, they enable customers to categorize resources by purpose, owner, environment, or other criteria.
2.5 | Termination Protection | You can prevent an instance from being terminated accidentally by someone using the AWS Management Console, the CLI, and the API. This feature is available for both Amazon EC2 instance store-backed and Amazon EBS-backed instances. Each instance has a DisableApiTermination attribute with the default value of false (the instance can be terminated through Amazon EC2). You can modify this instance attribute while the instance is running or stopped (in the case of Amazon EBS-backed instances).
2.6 | OS Configuration | SAP and AWS provide guidelines on the configuration required to run SAP for supported operating systems. Additional Security Hardening should also be implemented according to company guidelines. AWS recommends that these changes are applied as part of an automated deployment to ensure consistency between environments and that a configuration management system is in place to ensure that there is no “drift” from the standard. Refer to: 2578899 - SUSE Linux Enterprise Server 15: Installation Note 1944799 - SAP HANA Guidelines for SLES Operating System Installation
3 | Security
3.1 | AWS Access and MFA | AWS Identity and Access Management (IAM) enables you to manage access to AWS services and resources securely. Using IAM, you can create and manage AWS users and groups, and use permissions to allow and deny their access to AWS resources. Multi-factor authentication is highly recommended for privileged users
3.2 | IAM and Instance Profiles | AWS Identity and Access Management (IAM) enables you to manage access to AWS services and resources securely. Using IAM, you can create and manage AWS users and groups, and use permissions to allow and deny their access to AWS resources. SAP systems require access to the AWS CLI in order that the SAP DataProvider functions correctly, it may also be necessary to have access to an S3 bucket, stop/start instances or rely on other AWS Services. If this is done from the Instance, access should be provided via an IAM Instance Profile, rather than using Access keys which need to be rotated. Where possible that profile should be limited to only the functions required. The following details the Server Roles required for particular SAP-related functionality. Data Provider requirements are here: https://docs.aws.amazon.com/sap/latest/general/data-provider-intro.html. For Overlay and STONITH policies, refer to: https://documentation.suse.com/sbp/all/html/SLES4SAP-hana-sr-guide-PerfOpt-12_AWS/index.html#id-1.5.11.9.7.
3.3 | Security Groups and NACLs | A security group acts as a virtual firewall for your instance to control inbound and outbound traffic. When you launch an instance in a VPC, you can assign multiple security groups. Security groups act at the instance level, not the subnet level. Therefore, each instance in a subnet in your VPC could be assigned to a different set of security groups. A network access control list (ACL) is an optional layer of security for your VPC that acts as a firewall for controlling traffic in and out of one or more subnets. For SAP, the blog series VPC Subnet Zoning Patterns for SAP on AWS gives recommendations regarding Nested Security Groups (i.e. definitions which use Security groups as the source rather than CIDR ranges)
3.4 | Encryption | Amazon EBS encryption offers you a simple encryption solution for your EBS volumes without the need for you to build, maintain, and secure your own key management infrastructure. Amazon EFS offers the ability to encrypt at rest and in transit. Amazon S3 default encryption provides a way to set the default encryption behaviour for an S3 bucket. You can set default encryption on a bucket so that all objects are encrypted when they are stored in the bucket.
3.5 | OS Access / System Users | Controls should be put in place for OS Access and Privileged application users. Hardening guidelines for restricting remote login, strengthening password policies and rotation and controlling privileged access including cron, sudoers and umask should all follow best practise from SAP, Database and OS Vendors. Consideration should also be given to the process for ongoing control of joiners, movers and leavers.
3.6 | Security Logging and Alerting | Design Security logging approaches which capture metrics for real time actions and post-event analysis. This includes AWS services as well as application-based security logs. Integrate the flow of security events and findings into a notification and workflow system such as a ticketing system, a bug/issue system, or other security information and event management (SIEM) system.
4 | Performance
4.1 | Instance Sizing for Performance | Use SAP and AWS sizing and monitoring tools and to ensure instances are “right” sized on an on-going basis. Refer to the compute optimizer
4.2 | Storage Selection and layout | SAP HANA stores and processes all or most of its data in memory, and provides protection against data loss by saving the data in persistent storage locations. To achieve optimal performance, the storage solution used for SAP HANA data and log volumes should meet SAP's storage KPI. AWS has worked with SAP to certify both Amazon EBS General Purpose SSD (gp2 and gp3) and Provisioned IOPS SSD (io1 and io2) storage solutions for SAP HANA workloads. GP3 was certified for HANA workloads in May 2021
4.3 | Performance - Other | Any other performance or sizing related concerns.
5 | Resilience
5.1 | Requirements Definition | A company typically decides on an acceptable RTO (Recovery Time Objective) and RPO (Recovery Point Objective) based on the financial impact to the business when systems are unavailable. The company determines financial impact by considering many factors, such as the loss of business and damage to its reputation due to downtime and the lack of systems availability. IT organizations then plan solutions to provide cost-effective system recovery based on the RPO within the timeline and the service level established by the RTO (http://media.amazonwebservices.com/AWS_Disaster_Recovery.pdf)
5.2 | Architecture | A loosely coupled architecture helps you to create logical separation of systems and increased autonomy of components. It decreases the dependencies that components have on each other through standard communication and network channels.
5.3 | Failure Scenario Analysis | For each failure scenario, the resiliency requirements, acceptable data loss, and mean time to recover (MTTR) need to be proportionate to the criticality of the component and the business applications it supports. For the purpose of this analysis, we use the following definitions: High Availability as the ability to sustain a single failure with minimal impact to end users. Disaster Recovery is a scenario in which business would need to make a decision to invoke some kind of system recovery.
5.4 | Cluster Configuration | Operating System Vendors have worked with SAP and AWS to provide guides for the configuration of Pacemaker clusters on AWS
5.5 | Backups | Backups contain a copy of the data contained either in the database or file system and may be relied upon to reconstruct that data in the event of failure, corruption, deletion or as part of audit activities. It is important to ensure all components are backed up to a schedule which matches the criticality of the data, the rate of change and the likelihood that restore may be required. Database backups require that the data is in a consistent state. A requirement to recover a subset of the data or system should be considered.
6 | Cost Optimization
6.1 | Instance sizing for Cost | Amazon EC2 provides a wide selection of instance types optimized to fit different use cases. Instance types comprise varying combinations of CPU, memory, storage, and networking capacity and give you the flexibility to choose the appropriate mix of resources for your applications. Each instance type includes one or more instance sizes, allowing you to scale your resources to the requirements of your target workload.
6.2 | Instance Billing | There are many ways to pay for Amazon EC2 instances: On-Demand, Reserved Instances, Savings Plans and Spot Instances. You can also pay for Dedicated Hosts which provide you with EC2 instance capacity on physical servers dedicated for your use. Amazon EC2 Reserved Instances and Savings Plans allow you to reserve Amazon EC2 computing capacity for 1 or 3 years, in exchange for a significant discount (up to 75%) compared to On-Demand instance pricing. In addition, when Reserved Instances are assigned to a specific Availability Zone, they provide a capacity reservation, giving you additional confidence in your ability to launch instances when you need them
6.3 | Data Volume Management | Reduce data footprint to save costs by minimizing database size and other filesystem usage through regular housekeeping and reorganization activities.
6.4 | S3 and Snapshot Lifecycle Policies | Lifecycle rules can be used to define actions that you want Amazon S3 to take during an object's lifetime (for example, transition objects to another storage class, archive them, or delete them after a specified period of time). Snapshots should be managed via the Amazon Data Lifecycle Manager or other means.
7 | Operations
7.1 | Runbooks | Operational runbooks should be used to document routine activities in the cloud.
7.2 | Automation and DevOps | AWS provides a set of flexible services designed to enable companies to more rapidly and reliably build and deliver products using AWS and DevOps practices. These services simplify provisioning and managing infrastructure, deploying application code, automating software release processes, and monitoring your application and infrastructure performance.
7.3 | Support Calendar and Patching Process | Create a SAP landscape roadmap visualising your key SAP lifecycle events and operational upkeep - patching, software upgrades, migrations and re-platforming if required. Communicate this lifecycle calendar to business and technical stakeholders. Plan investment to fund these SAP lifecycle activities/projects. Plan in advance with your business stakeholders where maintenance windows can occur and downtime or restarts will be required.
7.4 | HA/DR Testing | Periodically test resilience against critical failure scenarios to prove that software and procedures result in a predictable outcome. Evaluate any changes to architecture, software, or support personnel to determine if additional testing is necessary.

## Sheet3 (hidden)
Review for Improvement